## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
User story 1 | 1 | 27/05/2024 | Did some research, then created splash page
User story 2 | 1 | 27/05/2024 | Created basic structure of overview page.
User story 2 | 2 | 28/05/2024 | Read up on Flutter search bars and listviews. Figured out how to load .svg icons into project
User story 2 | 1 | 28/05/2024 | Created House class with JSON function.
User story 2 | 4 | 28/05/2024 | Built and styled Card for ListView builder on home page (this took longer because I got a bit carried away trying to make it look exactly like the workflow design) Added fonts to .yaml file
User story 2 | 1 | 29/05/2024 | Implemented BottomNavigationBar.
User story 2 | 2 | 30/05/2024 | Finished BottomNavigationBar on both pages. Implemented Location Permission functionality.
User story 2 | 1 | 30/05/2024 | Set up API functions. Incorporated FutureBuilder into home_page.
User story 2 | 1 | 31/05/2024 | Dubugged some API call issues using PostMan.
User story 4 | 1 | 2024-06-03 | Created About page. Getting the hyperlink to work took longer than expected. Had trouble with url_launcher library.
User story 1 | 1 | 2024-06-03 | Fixed issue where home page shows NULL error while loading.
User story 3 | 1 | 2024-06-04 | Created and styled house details page.
User story 3 | 2 | 2024-06-04 | Built map functionality. Had some trouble with android/iOS permissions here which added some time here.
User story 2 | 1 | 2024-06-04 | Completed search functionality.
User story 2 | 1 | 2024-06-04 | Implemented price filter. Aesthitic and code clean up.
User story 2 | 1 | 2024-06-05 | Did some testing with the location permission functionality. Debugged a few issues that were found.
Bonus | 2 | 2024-06-07 | Added sliders to filter. | X
Bonus | 1 | 2024-06-07 | Added sizer measurements to some pages. Handled 'No Internet'. | X
Bonus | 2 | 2024-06-07 | Added 3D model floor plan. | X
Total amount of hours | 22